## Demand plan
Demand registration from Avni — summary
In one line: Avni creates the Demand, the integration service pushes it to Salesforce once, Salesforce gives it a code and owns it from then on.
Section | Item | Detail | Owner | Status | Notes / Answer
WHY WE'RE DOING THIS
Salesforce licences are expiring for some Goonj partner teams. Today a Demand can only be created in Salesforce, so those teams would lose the ability to raise one at all. This lets them start a Demand in Avni instead.
Partners who keep their Salesforce licences carry on exactly as today — nothing about that flow changes.
HOW IT WORKS
| Step 1 | A field team fills in the Demand form in Avni.
| Step 2 | The Data POC ticks 'Verified' — that's what triggers the send to Salesforce.
| Step 3 | Salesforce creates the record and generates the Demand Code.
| Step 4 | Salesforce's ID comes back and is saved onto the Avni record. (Whether this happens in the same exchange or on the next sync is still to be confirmed — see Q2.)
| Step 5 | From then on Salesforce owns it. Status changes (Approved, DA, DV, DPV) flow down into Avni automatically, using the sync that already exists today.
WORTH KNOWING
| Demand Code always comes from Salesforce | Avni can't generate it — it needs a per-account counter only Salesforce maintains. Users won't see a code immediately; it appears once the round trip completes. Field teams need telling, or it looks like a bug.
| The push happens once | After Salesforce's ID is saved onto the Avni record, we never push that Demand again. Corrections are made in Salesforce from that point.
| Salesforce's endpoint must be an 'upsert' | Keyed on the Avni record's own ID. That is what stops a network retry creating two Demands with two different codes.
| Editing locks when 'Approved' reaches the phone | Per the requirement sheet. There's a window before that where edits are allowed but won't reach Salesforce, so the form should warn during it.
| Duplicate checking happens in Salesforce | Not in Avni.
WHO DOES WHAT
| Build the upsert endpoint that accepts a Demand | Doesn't exist today. On the critical path — nothing goes live without it. | Goonj / SF | Not started
| Generate the Demand Code, and run duplicate checking | On the same endpoint. | Goonj / SF | Not started
| Confirm the final picklists | Disaster Type, Target Community, and which Kit Types have sub-types. | Goonj | Not started
| Build the Demand form | Fields, line items, validations, verification checkbox, edit rule, role gating. | Avni | Not started
| Build the integration | Watch Avni, push to Salesforce, save the ID back, handle errors. | Avni | Not started
ORDER OF WORK
| 1. Agree | Answer the open questions below. | Both | Not started
| 2. Build | Goonj's endpoint, our form, our integration code — these can run in parallel. | Both | Not started
| 3. Test | Against a stub first, then a real Salesforce staging org, then end to end. | Both | Not started
| 4. Deploy | Salesforce first, integration second, wait 1-2 days, open registration last. | Both | Not started
| 5. Watch | Confirm the first real Demands complete the full round trip. | Both | Not started
OPEN QUESTIONS
| Q1. Who is building the Salesforce upsert endpoint, and by when? | BLOCKER. It doesn't exist today and nothing goes live without it. Longest lead time, so start here. | Goonj / SF | Open
| Q2. Does Salesforce return the Demand Code in the response to our push, or only on a later sync? | Decides whether the user sees their Demand Code after one sync cycle or two. Needs settling before we build the converter. | Goonj / SF | Open
| Q3. What are the final picklists? | Disaster Type has no options listed at all; Target Community is partial and marked TBD; and only 3 of the 14 Kit Types (CFW, Marriage Kits, Vaapsi) have sub-types documented — do the others have any? BLOCKER: both the Avni form and the field mapping depend on these. | Goonj | Open
| Q4. Which user groups get access to Demand registration, and what can each do — create, edit, void? | Registration is off for every group by default, so we need the specific list and the permissions per group before anything can be switched on. | Both | Open
ALREADY SETTLED
| Salesforce returns the Demand ID on every call | Including when it recognises a Demand it already has. The Avni side uses it to update the record that already exists — setting the ID on an Avni-created Demand, updating in place for ones already linked — never creating a new one. |  | Settled
| The edit lock keys off the Approved status | Not the Demand Code, per the requirement sheet's 'Once Demand status as Approved'. This leaves a deliberate window in which Avni edits do not reach Salesforce, so the form should warn during it. |  | Settled
ROUGH ESTIMATE
| Avni form & config | ~3 person-days | Avni
| Integration service | ~5.5 person-days | Avni
| QA, UAT and go-live | ~8.5 person-days | Avni
| TOTAL | ~17 person-days | Avni
| Scope note | Avni-side effort only — Goonj's Salesforce work is NOT included, and that sits on the critical path. Development depends on when the Salesforce endpoint is available, and when the forms and other details are clear enough to be picked up.